## Project Data
Project Name | Route planning App
Online team meeting | https://tu-berlin.zoom-x.de/j/63201367987?pwd=pwLP7eO90NCqkHyHE0cssfqZA0PwDl.1
Production system (if any)
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2025ss03-route-planning-app
GitHub feature board | https://github.com/orgs/amosproj/projects/81
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/85
Team T-shirt (white) | https://www.shirtinator.de/loadBasket/PNnhXl2COPF
Team T-shirt (black) | ...
Additional materials | ...
Team maling list | oss-amos-proj3@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Sandt | Eloi | eloinoel | eloi.sandt@campus.tu-berlin.de
Justus | Kleinau | jkleinau | j.kleinau@campus.tu-berlin.de
Harms | Finn | innif
Karkani | Despoina | dkarkani | despoina.karkani@campus.tu-berlin.de
Karmokar | Subroto | SK-Subroto | subroto.karmokar@fau.de
Dutta | Arkadeep | arkadeepberlin | arkadeep.dutta@campus.tu-berlin.de
Uddin | Md Fahim | fahimu10 | fahim.uddin@fau.de
Khanam | Faria Rahman | fariarahman15 | faria.khanam@fau.de
Summerer | Felix | SUFelix | felix.summerer@fau.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2025-04-16 |  | Despina | Everyone else | N/A | Eloi
2 | 2025-04-23 | Despina | Arkadeep | Everyone else | Finn | Eloi
3 | 2025-04-30 | Arkadeep | Despina | Everyone else | Justus | Eloi
4 | 2025-05-07 | Despina | Arkadeep | Everyone else | Faria | Eloi
5 | 2025-05-14 | Arkadeep | Despina | Everyone else | Subroto | Eloi
6 | 2025-05-21 | Despina | Arkadeep |  | Felix | Eloi
7 | 2025-05-28 | Arkadeep | Despina |  | Fahim | Eloi | Mid-term due
8 | 2025-06-04 | Despina | Arkadeep |  | Subroto | Eloi
9 | 2025-06-11 | Arkadeep | Despina |  | Faria | Eloi
10 | 2025-06-11 | Despina | Arkadeep |  | Justus | Eloi
11 | 2025-06-18 | Arkadeep | Despina |  | Felix | Eloi
12 | 2025-06-25 | Despina | Arkadeep |  | Fahim | Eloi
13 | 2025-07-02 | Arkadeep | Despina |  | Subroto | Eloi
14 | 2025-07-09 | Despina | Arkadeep |  | Faria | Eloi | Demo day!
15 | 2025-07-16 | Arkadeep |  |  |  | Eloi | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Have an enjoyable experience in working together
learn from each other
Our teams tries to create tangible progress with the application every week
Complete ECTS and get good grade
Provide a usefull solution to meisterwerk
Meeting norms | All team-meetings are mandatory unless a valid reason is communicated in advance
be on time to value each other's time
Ask questions if your are not clear on something.
The meeting starts on time, even if not all members are present yet
Camera On :)
Working norms | Team members should be open to feedback and view it as a growth opportunity
We use feature, development and fix-branches in git
When we face problems or fail to reach our goals, we should communicate that as soon as possible
Always help each other!
agree on who does what and keep track of it
Follow coding conventions
Openly communicate working capacity, so work can be attributed accordingly
Keep each other updated about progress
Coordination norms | The Product owners for Review and Planning respectively switch every week
The PO's (at least, devs are always welcome to join) meet with the industry partner at regular intervals and communicate feature requests to the rest of the team
When facing decisions that cant be resolved in a discussion, we put it to vote
keep essential information and links to tools centralised in one place (seperate discord channel)
Communication norms | Use the communication tools that we have. In our case a Discord Server
We should answer within one day
There are no stupid questions!
Communicate respectfully and let everybody speak out
Respect each others opinions, we are all here to learn :)
constructive criticism, talk about solutions
communicate illnesses and expected work downtime and what it means for others
Smaller problems with persons in thew group should be voiced in meetings, larger concerns should be discussed in a one-on-one call first
Consideration norms | Each task will have a primary owner(s) and a reviewer to ensure accountability and quality.
Talk about the problem, talk with the roles, get the context. Communication is very important to understand everything
prefer to speak in public over speaking privately?
Cont. improvement norms | Keep 15 minutes atleast for Sprint retrospective
Give constructive feedback on Pull Requests
Rewards
One evening/afternoon/whatever of fun online games
Sanctions
10 minutes of mandatory guided meditation… with a goat yoga video soundtrack
A silly video-filter has to be activated for the next meeting
Signatures
Scrum Master | Eloi Sandt
Product owner | Arkadeep Dutta
Product owner | Despina Karkani
Software developer
Software developer | Subroto Karmokar
Software developer | Faria Rahman Khanam
Software developer | Md Fahim Uddin
Software developer | Finn Harms
Software developer | Justus Kleinau
Software developer | Felix Summerer

## Product Goal
Product Vision | Project Mission
To build an intelligent, automated route optimization tool that empowers organizations to efficiently assign appointments to field workers—optimizing for time, cost, and resource usage—while maximizing overall operational efficiency and service quality | The mission of this project is to create an MVP for the AMOS Route Optimizer. Core functionality will include uploading appointment data, generating an optimized route plan based on efficiency criteria (e.g., time, cost, resource usage), and displaying the resulting plan on an interactive map interface.

## Product Glossary
Term | Definition

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | None
5 | Finalize the optimization trigger flow, integrate distance calculations, and implement preprocessing to detect potential solver issues before execution.
6 | Connect backend route data to the frontend, visualize the full daily and worker plans, and introduce servicetime customization in both backend and UI.
7
8
9
10
11
12
13
14
15

## DoD Definitions
feature Specific | Sprint Specific | Project release
Frontend and backend components for the feature are implemented and integrated Feature is reviewed via code review (e.g., pull request approved) Feature is merged into the development branch without breaking other functionalities The feature is demo-ready and accepted by the Product Owner | The app builds and runs successfully in a clean environment All sprint backlog items marked as "Done" meet the Feature DoD Demo conducted with functioning features shown via "show and tell" in Sprint Planning session by the developers Release notes are created and shared (e.g., summary in planning document or GitHub) Velocity is tracked and recorded | All core MVP functionality is implemented and passes acceptance tests Optimized route output is visualized on the map using real user inputs Documentation is complete (README.md, user guide, build instructions) System passes testing across common browsers/environments Mid- and final release plans are fulfilled Build process video and required deliverables are uploaded

## Velocity Tracking
Sprint # | Story Points Realized
1
2 | 14
3 | 44
4 | 33
5 | 32
6
7
8
9
10
11
12
13
14
15
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 123 | 123
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 | Basic formal documentation requirements |  | 0 | 123 | 0 | 123
2 | Set up backend, frontend, and upload infrastructure to support the route planning flow. |  | 14 | 123 | 11 | 123
3 | Complete the foundation for file upload, schema validation, and routing structure on both backend and frontend to prepare for full route processing. |  | 44 | 109 | 36 | 112
4 | Integrate and run the initial optimization plan, connect validated input data, and prepare the frontend for dynamic interaction with editable and visual route elements. |  | 33 | 65 | 37 | 76
5 | Finalize the optimization trigger flow, integrate distance calculations, and implement preprocessing to detect potential solver issues before execution. |  | 32 | 32 | 0 | 39
6 | Connect backend route data to the frontend, visualize the full daily and worker plans, and introduce servicetime customization in both backend and UI. |  | 0
Features
1 | Basic formal documentation requirements | None
2 | Set up backend, frontend, and upload infrastructure to support the route planning flow. | Set up Backend | 2 |  | 3
|  | Save & Load Scenarios from JSON | 5 |  | 3
|  | Set Up CI/CD Pipeline | 5 |  | 3
|  | Set up Front End | 2 |  | 2
3 | Complete the foundation for file upload, schema validation, and routing structure on both backend and frontend to prepare for full route processing. | Agreement on basic structure – Frontend Backend | 8 |  | 8
|  | Validate Addresses via Google Maps Geocoding API | 8 |  | 5
|  | Implement Start and Finish Address Fields (Business data) | 1 |  | 1
|  | Add Worker Count Slider Component | 1 |  | 1
|  | Create “Start Optimization” Button | 1 |  | 1
|  | Create a routing structure on the frontend | 3 |  | 3
|  | Build File Upload Component | 3
|  | Docker File Creation | 3 |  | 3
|  | Excel File Upload Functionality | 3 |  | 3
|  | Convert Uploaded Excel File to JSON | 5 |  | 3
|  | JSON Schema Validation for Uploaded File | 3 |  | 3
|  | Create distance matrix from the uploaded address | 5 |  | 5
4 | Integrate and run the initial optimization plan, connect validated input data, and prepare the frontend for dynamic interaction with editable and visual route elements. | Migrate Frontend Components to ShadcnUI and TailwindCSS | 2 |  | 3
|  | Map Business Data Sheet and Appointment Data to the UI | 3 |  | 5
|  | Move Editable Inputs and Start Button to Map View | 3 |  | 3
|  | Implement Basic Optimization Plan: First Draft | 8 |  | 8
|  | Connecting Worker Address Validation and Distance Matrix | 3 |  | 3
|  | Implement Basic Map View with Location Points Only | 8 |  | 8
|  | Add Calendar View with Daily Appointment Overview | 3 |  | 5
|  | Explore Options for Handling Faulty Addresses from Uploaded Files in the UI | 3 |  | 2
5 | Finalize the optimization trigger flow, integrate distance calculations, and implement preprocessing to detect potential solver issues before execution. | Implement Preprocessing Logic to Detect Potential Solver Failures: First Draft | 5
|  | Implement Distance Calculation in the Route Optimization | 3 |  | 0
|  | Project Optimized Routes on the Map View | 8 |  | 0
|  | Prepare Application for Deployment in Industry Partner’s AWS Environment (Backend) | 8 |  | 0
|  | Allow User to Uncheck Faulty Addresses and Proceed with Optimization | 5 |  | 0
|  | Connect “Start Optimization” Button to Backend Optimization Trigger | 3 |  | 0
6 | Connect backend route data to the frontend, visualize the full daily and worker plans, and introduce servicetime customization in both backend and UI. | Implement Frontend Visualization for Errors Raised in Preprocessing | 0 |  | 0
|  | Display Daily Plan as a List/Table with Export Option | 0 |  | 0
|  | Display and Export Individual Worker Plans | 0 |  | 0
|  | Integrate Solver API Output to Frontend for Route Visualization | 0 |  | 0
|  | Allow User to Configure Service Time per Appointment (With Default Fallback) | 0 |  | 0
|  | Create Space and Distinguish between Service Time and Appointment Time in Backend | 0 |  | 0
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License | Comment
| Programming Language for Backend | Python | 3.11 | Python Software Foundation (PSF) License
| API Framework for Backend API | FastAPI | 0.103.1 | MIT License
| Route Optimization in Backend | Google OR | 9.7 | Apache 2.0
| Get Distance-Matrix between points for routing | Google Maps API | N/A | Commercial
| Programming Language for Frontend | Typescript | 5.7.2 | Apache 2.0
| Framework for Frontend | ReactJS | 19.01 | MIT License
| UI-Components for Frontend | Shadcm UI | 2.5.0 | MIT License
| CSS Framwork for Frontend | TailwindCSS | 4 | MIT License

## Planning Poker
Last Name | First Name | Value
Last Name | #REF! |  | #DIV/0! | #DIV/0!
#REF! | #REF!
Justus | Kleinau
#REF! | #REF!
Harms | Finn |  | 0 | No size
Karkani | Despoina |  | 1 | Trivial size
Karmokar | Subroto |  | 2 | Small size
Uddin | Md Fahim |  | 3 | Medium size
Khanam | Faria Rahman |  | 5 | Large size
Summerer | Felix |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value