## Project Data
Project Name | Route planning App
Online team meeting | https://tu-berlin.zoom-x.de/j/63201367987?pwd=pwLP7eO90NCqkHyHE0cssfqZA0PwDl.1
Production system (if any)
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2025ss03-route-planning-app
GitHub feature board | https://github.com/orgs/amosproj/projects/81
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/85
Team T-shirt (white) | ...
Team T-shirt (black) | ...
Additional materials | ...
Team maling list | oss-amos-proj3@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Sandt | Eloi | eloinoel | eloi.sandt@campus.tu-berlin.de
Justus | Kleinau | jkleinau | j.kleinau@campus.tu-berlin.de
Wegele | Mike | mikewegele | mike.wegele@fu-berlin.de
Harms | Finn | innif
Karkani | Despoina | dkarkani | despoina.karkani@campus.tu-berlin.de
Karmokar | Subroto | SK-Subroto | subroto.karmokar@fau.de
Dutta | Arkadeep | arkadeepberlin | arkadeep.dutta@campus.tu-berlin.de
Uddin | Md Fahim | fahimu10 | fahim.uddin@fau.de
Khanam | Faria Rahman | fariarahman15 | faria.khanam@fau.de
Summerer | Felix | SUFelix | felix.summerer@fau.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2025-04-16 |  | Arkadeep | Everyone else | N/A | Eloi Sandt
2 | 2025-04-23 | Arkadeep | Despina | Everyone else | Finn | Eloi Sandt
3 | 2025-04-30 | Despina | Arkadeep | Everyone else | Subroto | Eloi Sandt
4 | 2025-05-07 | Arkadeep | Despina | Everyone else | Faria | Eloi Sandt
5 | 2025-05-14 | Despina | Arkadeep | Everyone else | Justus | Eloi Sandt
6 | 2025-05-21 | Arkadeep | Despina |  | Felix | Eloi Sandt
7 | 2025-05-28 | Despina | Arkadeep |  | Fahim | Eloi Sandt | Mid-term due
8 | 2025-06-04 | Arkadeep | Despina |  | Mike | Eloi Sandt
9 | 2025-06-11 | Despina | Arkadeep |  | Finn | Eloi Sandt
10 | 2025-06-11 | Arkadeep | Despina |  | Subroto | Eloi Sandt
11 | 2025-06-18 | Despina | Arkadeep |  | Faria | Eloi Sandt
12 | 2025-06-25 | Arkadeep | Despina |  | Justus | Eloi Sandt
13 | 2025-07-02 | Despina | Arkadeep |  | Felix | Eloi Sandt
14 | 2025-07-09 | Arkadeep | Despina |  | Fahim | Eloi Sandt | Demo day!
15 | 2025-07-16 | Despina |  |  | Mike | Eloi Sandt | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Have an enjoyable experience in working together
learn from each other
Our teams tries to create tangible progress with the application every week
Complete ECTS and get good grade
Provide a usefull solution to meisterwerk
Meeting norms | All team-meetings are mandatory unless a valid reason is communicated in advance
be on time to value each other's time
Ask questions if your are not clear on something.
The meeting starts on time, even if not all members are present yet
Camera On :)
Working norms | Team members should be open to feedback and view it as a growth opportunity
We use feature, development and fix-branches in git
When we face problems or fail to reach our goals, we should communicate that as soon as possible
Always help each other!
agree on who does what and keep track of it
Follow coding conventions
Openly communicate working capacity, so work can be attributed accordingly
Keep each other updated about progress
Coordination norms | The Product owners for Review and Planning respectively switch every week
The PO's (at least, devs are always welcome to join) meet with the industry partner at regular intervals and communicate feature requests to the rest of the team
When facing decisions that cant be resolved in a discussion, we put it to vote
keep essential information and links to tools centralised in one place (seperate discord channel)
Communication norms | Use the communication tools that we have. In our case a Discord Server
We should answer within one day
There are no stupid questions!
Communicate respectfully and let everybody speak out
Respect each others opinions, we are all here to learn :)
constructive criticism, talk about solutions
communicate illnesses and expected work downtime and what it means for others
Smaller problems with persons in thew group should be voiced in meetings, larger concerns should be discussed in a one-on-one call first
Consideration norms | Each task will have a primary owner(s) and a reviewer to ensure accountability and quality.
Talk about the problem, talk with the roles, get the context. Communication is very important to understand everything
prefer to speak in public over speaking privately?
Cont. improvement norms | Keep 15 minutes atleast for Sprint retrospective
Give constructive feedback on Pull Requests
Rewards
One evening/afternoon/whatever of fun online games
Sanctions
10 minutes of mandatory guided meditation… with a goat yoga video soundtrack
A silly video-filter has to be activated for the next meeting
Signatures
Scrum Master | Eloi Sandt
Product owner | Arkadeep Dutta
Product owner | Despina Karkani
Software developer | Mike Wegele
Software developer | Subroto Karmokar
Software developer | Faria Rahman Khanam
Software developer | Md Fahim Uddin
Software developer | Finn Harms
Software developer | Justus Kleinau
Software developer | Felix Summerer

## Product Goal
Product Vision | Project Mission
The reason of existence of the envisioned product (beyond this project). | The mission of this particular project (in the context of the product vision).

## Product Glossary
Term | Definition

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Optional
5 | Write your sprint goal here
6
7
8
9
10
11
12
13
14
15

## Velocity Tracking
Sprint # | Story Points Realized
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License | Comment

## Planning Poker
Last Name | First Name | Value
#REF! | #REF! | 5 | 5 | OK
#REF! | #REF! | 5
Justus | Kleinau
Wegele | Mike
Harms | Finn |  | 0 | No size
Karkani | Despoina |  | 1 | Trivial size
Karmokar | Subroto |  | 2 | Small size
Uddin | Md Fahim |  | 3 | Medium size
Khanam | Faria Rahman |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value